## Gantt Chart
Ontario Wildfire Impact & Forecasting Analytics - Project Gantt Chart
Assumption: Focused pace, 20+ hrs/week (~4 hrs/day, 5 days/week). Full timeline starts Jul 17, 2026; Sprint 1 extended +2 days for a locally-scheduled Airflow DAG. Academic & Independent Project — dates are planning estimates, not commitments.
Phase | Sprint / Epic | Start Date | End Date | Duration (business days) | Day Offset (from project start) | Status
Phase 0 | Requirements Gathering & Discovery | 2026-07-17 | 2026-07-20 | 2 | 0 | Complete
Phase 1 | Product Backlog & Sprint Planning | 2026-07-21 | 2026-07-22 | 2 | 2 | Complete
Phase 2 | Sprint 1: Data Foundation + Airflow DAG | 2026-07-23 | 2026-08-05 | 10 | 4 | Not started
Phase 3 | Sprint 2: Baseline Modeling | 2026-08-06 | 2026-08-10 | 3 | 14 | Not started
Phase 4a | Sprint 3: Univariate LSTM Fundamentals | 2026-08-11 | 2026-08-18 | 6 | 17 | Not started
Phase 4b | Sprint 4: Multivariate LSTM & Tuning | 2026-08-19 | 2026-08-26 | 6 | 23 | Not started
Phase 5 | Sprint 5: Evaluation & Retrospective | 2026-08-27 | 2026-09-01 | 4 | 29 | Not started
Phase 6 | Sprint 6: Tableau Story & Documentation | 2026-09-02 | 2026-09-09 | 6 | 33 | Not started
Formulas:
Duration (business days) = NETWORKDAYS([Start Date],[End Date])
Day Offset (from project start) = NETWORKDAYS(C5,[Start Date])-1

## Tools & Techniques
Tools & Techniques by Phase
Phase | Tools | Techniques / Methods | New Skill Being Validated?
Phase 0 : Requirements Gathering & Discovery | Markdown, web research (CWFIS, Environment Canada, Ontario.ca, Air Quality Ontario) | Project chartering, non-goals framing, risk identification, user-story writing | No : planning process, not a technical skill
Phase 1 : Product Backlog & Sprint Planning | Markdown / spreadsheet backlog, Git (repo scaffold) | Epic/story decomposition, estimation, Definition of Done authoring, sprint sequencing | No : Agile process skill, already familiar
Phase 2 : Sprint 1: Data Foundation + Airflow DAG | Python (pandas, NumPy), SQL (T-SQL/PostgreSQL), Git, Airflow (local scheduler), CWFIS WFS API, ECCC AQHI GeoMet API | Manual + automated data sourcing, star-schema (fact/dim) modeling, EDA, scheduled DAG design with failure handling | Partial : first end-to-end scheduled DAG in this portfolio, reinforcing verified Airflow familiarity
Phase 3 : Sprint 2: Baseline Modeling | Python (pandas, scikit-learn) | Naive-persistence baseline, moving-average baseline, RMSE/MAE evaluation setup | No : reinforcing verified skills
Phase 4a : Sprint 3: Univariate LSTM Fundamentals | Python, TensorFlow/Keras | LSTM conceptual fundamentals (gates, vanishing gradient), time-series windowing, univariate LSTM, dropout/regularization | YES : first hands-on TensorFlow/Keras + LSTM implementation
Phase 4b : Sprint 4: Multivariate LSTM & Tuning | Python, TensorFlow/Keras, scikit-learn (scaling) | Multivariate feature engineering (AQI, fire count, temperature, wind), lookback-window design, hyperparameter tuning | YES : multivariate deep learning, still being validated
Phase 5 : Sprint 5: Evaluation & Retrospective | Python (matplotlib/seaborn), Excel | Honest LSTM-vs-baseline comparison across cities, error analysis (incl. underperformance), Agile retrospective | No : but validates whether Phase 4 skills actually held up
Phase 6 : Sprint 6: Tableau Story & Documentation | Tableau, Markdown / Word | Data storytelling & dashboard design, technical writing (README, methodology), public-facing summaries grounded in demonstrated work | Partial : first Tableau story of this scope

## Timeline Summary
Timeline Summary
Pace assumption | Focused, 20+ hrs/week (~4 hrs/day, 5 days/week)
Project start | Friday, July 17, 2026 (Phase 0, complete)
Sprint work begins | Tuesday, July 21, 2026 (Phase 1, complete)
Scope change | Added locally-scheduled Airflow DAG to Sprint 1 — extended Sprint 1 from 8 to 10 days
Estimated project end | Wednesday, September 9, 2026 (Phase 6 complete)
Total business days (Phases 0–6) | 39 business days (~8 calendar weeks)
Framing | Academic & Independent Project — dates are planning estimates, self-paced, not fixed commitments